## Master RAID Tracker
ID | Track | Type | Description | Owner | Date Logged | Due for Closure on | Status | Impact | Mitigation
A1 | Program | Action Item | Finalize and onboard Solution Architect | Global Delivery President | 2026-05-15 | 2026-05-20 | Open
A2 | Program | Action Item | Finalize and onboard Technical Architect | Global Delivery President | 2026-05-15 | 2026-05-20 | Open
A3 | Program | Action Item | Finalize and onboard Data Migration Lead | Global Delivery President | 2026-05-15 | 2026-05-20 | Open
A4 | Program | Action Item | Share named resource profiles and availability confirmation | Implementation Program Manager | 2026-05-15 | 2026-05-18 | Open
A5 | Program | Action Item | Launch automotive domain enablement sessions for all delivery members | Implementation Program Manager | 2026-05-15 | 2026-05-20 | Open
A6 | Program | Action Item | Deploy automotive domain consultant into discovery workshops | Global Delivery President | 2026-05-15 | 2026-05-20 | Open
A7 | Program | Action Item | Publish revised discovery and POC recovery plan | Implementation Program Manager | 2026-05-15 | 2026-05-19 | Open
A8 | Program | Action Item | Establish daily internal war-room governance | Implementation Program Manager | 2026-05-15 | 2026-05-16 | In Progress
A9 | Program | Action Item | Start twice-weekly customer checkpoint reviews | Customer PM & Implementation PM | 2026-05-15 | 2026-05-16 | In Progress
A10 | Program | Action Item | Share risk and dependency tracker with mitigation actions | Implementation Program Manager | 2026-05-15 | 2026-05-18 | Open
A11 | Program | Action Item | Improve workshop preparation and review process | Implementation Program Manager | 2026-05-15 | 2026-05-16 | In Progress
A12 | Program | Action Item | Executive review of stabilization progress every 48 hours | Global Delivery President | 2026-05-15 | 2026-05-16 | In Progress
D1 | Program | Decision | Program classified as Tier‑1 strategic delivery initiative by implementation leadership. |  | 2026-05-15 | 2026-05-15 | Closed
D2 | Program | Decision | Executive-level monitoring to continue until stabilization. |  | 2026-05-15 | 2026-05-15 | Closed
D3 | Program | Decision | Automotive domain enablement to become mandatory for all delivery members. |  | 2026-05-15 | 2026-05-15 | Closed
D4 | Program | Decision | Critical staffing closures to be completed within one week. |  | 2026-05-15 | 2026-05-15 | Closed
D5 | Program | Decision | Recovery plan to be reviewed in next weekly governance meeting. |  | 2026-05-15 | 2026-05-15 | Closed
R1 | Program | Risk | Delay in staffing critical roles | Implementation Program Manager | 2026-05-15 | 2026-05-22 | Open | Discovery and architecture delays | Executive escalation and prioritized onboarding
R2 | Program | Risk | Lack of automotive domain knowledge | Implementation Program Manager | 2026-05-15 | 2026-05-22 | Open | Reduced workshop effectiveness | Structured domain training and domain SME support
R3 | Program | Risk | Customer confidence erosion | Global Delivery President | 2026-05-15 | 2026-05-22 | Open | Governance escalation and delivery scrutiny | Increased transparency and executive oversight
R4 | Program | Risk | Discovery delays impacting downstream phases | Implementation Program Manager | 2026-05-15 | 2026-05-22 | Open | Compression of sprint rollout timeline | Parallel execution and recovery planning
QM-1 | Quality Management | Action Item | Engage certified automotive domain translator/interpreter for all process documents. Target: 100% translation of backlog within 5 business days. | Impl. PM | 2026-08-15 | 2026-08-20 | Open
QM-2 | Quality Management | Action Item | Immediately backfill BA vacancy—deploy available internal BA from Part & BOM track (now stable) on 50% dual allocation to Quality workshops. | Impl. PM | 2026-08-15 | 2026-08-18 | Open
QM-3 | Quality Management | Action Item | Run parallel workshops—two simultaneous sessions per week (English + translated document sets) to recover the 3-week lag in 10 working days. | Quality Lead | 2026-08-15 | 2026-08-22 | Open
QM-4 | Quality Management | Action Item | Pre-validate translated documents with customer business owner before each workshop to reduce rework loops. | Customer PM | 2026-08-15 | Ongoing | Open
QM-5 | Quality Management | Action Item | Publish revised Quality track schedule with recovery milestones and share with steering committee. | Impl. PM | 2026-08-15 | 2026-08-19 | Open
SC-1 | Supplier Collaboration | Action Item | Escalate supplier availability blockage to customer CXO / executive sponsor. Mandate named supplier SMEs with $\ge$ 40% time commitment via formal SLA. | Cust. Exec Sponsor | 2026-08-15 | 2026-08-18 | Open
SC-2 | Supplier Collaboration | Action Item | If CXO escalation yields no resolution within 3 days formally recommend structured deferral of this track to M10 with revised Phase 3 dependencies documented. | Impl. PM | 2026-08-15 | 2026-08-21 | Open
SC-3 | Supplier Collaboration | Action Item | In parallel: complete all supplier collaboration solution design with customer proxy SMEs to avoid further design delays once suppliers engage. | Solution Arch | 2026-08-15 | 2026-08-22 | Open
SC-4 | Supplier Collaboration | Action Item | Document full dependency map of Supplier Collaboration on Quality & Change tracks. Present impact to steering committee if deferral is chosen. | Impl. PM | 2026-08-15 | 2026-08-19 | Open
SC-5 | Supplier Collaboration | Action Item | Prepare two plans for steering committee: (A) Accelerated delivery if SMEs secured (B) Controlled deferral roadmap to M10 with risk summary. | Impl. PM | 2026-08-15 | 2026-08-22 | Open
INT-1 | Integration - All | Action Item | Convene emergency integration war-room: Solution Architect + downstream system leads (SAP NX Cadence) + vendor connector owners. Daily 60-min stand-up starting 16-Aug. | Impl. PM | 2026-08-15 | 2026-08-16 | Open
INT-2 | Integration - SAP | Action Item | Finalize data exchange model (BOM structure ECN payload material master fields). Customer ERP team and PLM architect to sign off jointly. Hard deadline: 19-Aug. | Sol. Arch | 2026-08-15 | 2026-08-19 | Open
INT-3 | Integration - SAP | Action Item | Run technical approach decision workshop with SAP Basis middleware (MuleSoft/BTP) team and PLM team. Document agreed approach and get written acceptance from SAP team lead. | Tech Arch | 2026-08-15 | 2026-08-20 | Open
INT-4 | Integration - NX | Action Item | Inventory all version compatibility gaps between PLM platform and NX CAD versions in use. Engage NX vendor for official compatibility matrix. Identify if hotpatch request can be fast-tracked. | NX Lead | 2026-08-15 | 2026-08-19 | Open
INT-5 | Integration - NX | Action Item | Escalate to NX vendor account manager for private hotpatch access or pre-release build to unblock integration layer. Document escalation in writing. | Impl. PM | 2026-08-15 | 2026-08-18 | Open
INT-6 | Integration - Cadence | Action Item | Engage Cadence vendor connector team for integration specification and confirm connector version available for target PLM version. Get written confirmation or documented gap. | Cadence Lead | 2026-08-15 | 2026-08-20 | Open
INT-7 | Integration - All | Action Item | Publish integration dependency & blocker register to steering committee with RAG status per integration point. (Template: Blocker ¦ Root Cause ¦ Owner ¦ Resolution Date ¦ Workaround). | Impl. PM | 2026-08-15 | 2026-08-22 | Open
INT-8 | Integration - Joint | Action Item | Conduct Integration risk review session: classify each blocker as Resolvable (with date) vs Irresolvable. Document workaround for each irresolvable item. | Sol. Arch | 2026-08-15 | 2026-08-25 | Open
INT-9 | Integration - Joint | Action Item | For irresolvable risks: prepare workaround proposals (e.g. file-based interim exchange manual sync processes phased go-live without integration middleware fallback patterns). | Tech Arch | 2026-08-15 | 2026-08-26 | Open
INT-10 | Integration - Joint | Action Item | Present full risk register + workaround proposals to executive steering committee for approval. Obtain sign-off on workarounds or additional escalation path. | Impl. PM | 2026-08-15 | 2026-08-27 | Open
INT-11 | Integration - Joint | Action Item | Revise integration delivery schedule based on approved workarounds. Confirm revised integration milestones and impact on Phase 3 adoption timeline. | Impl. PM | 2026-08-15 | 2026-08-29 | Open
DM-1 | Data Migration | Action Item | Generate synthetic PLM data set using open-source data fabrication tools (e.g. Faker Mimesis custom scripts) modelled on the agreed target data schema. Cover part masters BOM structures ECNs attributes. | DM Lead | 2026-08-15 | 2026-08-18 | Open
DM-2 | Data Migration | Action Item | Request anonymised production data extracts from customer. Use data masking / PII scrubbing tools on customer side to provide structurally real but privacy-safe records for migration testing. | Cust. DBA | 2026-08-15 | 2026-08-20 | Open
DM-3 | Data Migration | Action Item | Use existing 90% completed mapping to create a mock legacy extract in the source system format. Populate with synthetic values to simulate full volume migration for FTL testing. | DM Lead | 2026-08-15 | 2026-08-19 | Open
DM-4 | Data Migration | Action Item | Define acceptance criteria for synthetic data quality. Once real sample extract is available run delta comparison to validate synthetic data adequacy and calibrate ETL scripts. | QA Lead | 2026-08-15 | 2026-08-22 | Open
DM-5 | Data Migration | Action Item | Close remaining 10% mapping gap using customer business analyst (BA deployed from stable Part & BOM track) + available documentation. | BA / DM Lead | 2026-08-15 | 2026-08-20 | Open
DM-6 | Data Migration | Action Item | Evaluate and procure a purpose-built PLM data migration tool (e.g. XPDL Migrate4PLM or platform-native migration utilities). Conduct rapid PoC within 3 days. | DM Lead | 2026-08-15 | 2026-08-18 | Open
DM-7 | Data Migration | Action Item | If commercial tool procurement is blocked deploy open-source ETL framework (Apache NiFi or Talend Open Studio) configured for PLM source/target schema. | Tech Arch | 2026-08-15 | 2026-08-19 | Open
DM-8 | Data Migration | Action Item | Implement automated migration reconciliation checks: record count validation attribute completeness BOM structure integrity and delta report after each test run. | QA Lead | 2026-08-15 | 2026-08-22 | Open
DM-9 | Data Migration | Action Item | Immediate: Engage staffing partner / bench resources to deploy 2 PL/SQL-capable developers by 20-Aug. Require automotive PLM data migration experience. | Delivery VP | 2026-08-15 | 2026-08-20 | Open
DM-10 | Data Migration | Action Item | Onboarding sprint (Days 1–3): New developers to review existing ETL scripts mapping docs and test outputs. Pair with remaining DM team member for knowledge transfer. | DM Lead | 2026-08-15 | 2026-08-22 | Open
DM-11 | Data Migration | Action Item | Upskill delivery team on platform-native migration APIs in parallel—reduce pure PL/SQL dependency by adopting platform SDK-based migration approach where available. | Tech Arch | 2026-08-15 | 2026-08-22 | Open
DM-12 | Data Migration | Action Item | Deploy cloud-based developer on-demand resource (AWS/Azure marketplace) as a bridge while permanent hire is finalised. Cost to be approved by delivery VP. | Delivery VP | 2026-08-15 | 2026-08-18 | Open
DM-13 | Data Migration | Action Item | Conduct team confidence-building session: walkthrough of synthetic data migration success share test results define clear individual ownership of each migration object type. | DM Lead | 2026-08-15 | 2026-08-22 | Open
DM-14 | Data Migration | Action Item | Establish weekly DM-specific war-room: DM Lead + Tech Arch + QA Lead + customer DBA. Track % records migrated defects per run blocker status. | Impl. PM | 2026-08-15 | 2026-08-19 | Open