# Automotive PLM Consolidation Program

## Weekly Governance Review Meeting Details

Program: Automotive PLM Consolidation – 18 Month Roadmap
Meeting Type: Weekly Steering & Governance Review
Date: 15-May-2026
Scheduled Duration: 30 Minutes
Actual Duration: 45 Minutes
Program Status: RED

# Agreed Recovery Action Plan

## One Week Stabilization Objectives before next review meeting

The following stabilization objectives were agreed to be completed within one week:

- Close all critical staffing gaps.

- Establish confidence recovery plan.

- Improve workshop readiness.

- Launch automotive domain enablement.

- Publish revised discovery and POC recovery timeline.

# Next Review Meeting

| Item | Details |
| --- | --- |
| Meeting | Weekly Governance Review |
| Proposed Date | 22-May-2026 |
| Focus Area | Recovery Plan Validation & Staffing Closure |
| Expected Outcome | Program stabilization progress review |

# Action Items

| ID | Action Item | Owner | Due Date (starting 15/May/2026) | Status |
| --- | --- | --- | --- | --- |
| A1 | Finalize and onboard Solution Architect | Global Delivery President | Within 5 business days | Open |
| A2 | Finalize and onboard Technical Architect | Global Delivery President | Within 5 business days | Open |
| A3 | Finalize and onboard Data Migration Lead | Global Delivery President | Within 5 business days | Open |
| A4 | Share named resource profiles and availability confirmation | Implementation Program Manager | Within 3 business days | Open |
| A5 | Launch automotive domain enablement sessions for all delivery members | Implementation Program Manager | Within 5 business days | Open |
| A6 | Deploy automotive domain consultant into discovery workshops | Global Delivery President | Within 5 business days | Open |
| A7 | Publish revised discovery and POC recovery plan | Implementation Program Manager | Within 4 business days | Open |
| A8 | Establish daily internal war-room governance | Implementation Program Manager | Immediate | In Progress |
| A9 | Start twice-weekly customer checkpoint reviews | Customer PM & Implementation PM | Immediate | In Progress |
| A10 | Share risk and dependency tracker with mitigation actions | Implementation Program Manager | Within 3 business days | Open |
| A11 | Improve workshop preparation and review process | Implementation Program Manager | Immediate | In Progress |
| A12 | Executive review of stabilization progress every 48 hours | Global Delivery President | Immediate | In Progress |