## Quality Management
Action ID | Action Item Description | Target Date | Owner
QM-1 | Engage certified automotive domain translator/interpreter for all process documents. Target: 100% translation of backlog within 5 business days. | 2026-08-20 | Impl. PM
QM-2 | Immediately backfill BA vacancy—deploy available internal BA from Part & BOM track (now stable) on 50% dual allocation to Quality workshops. | 2026-08-18 | Impl. PM
QM-3 | Run parallel workshops—two simultaneous sessions per week (English + translated document sets) to recover the 3-week lag in 10 working days. | 2026-08-22 | Quality Lead
QM-4 | Pre-validate translated documents with customer business owner before each workshop to reduce rework loops. | Ongoing | Customer PM
QM-5 | Publish revised Quality track schedule with recovery milestones and share with steering committee. | 2026-08-19 | Impl. PM

## Supplier Collaboration
Action ID | Action Item Description | Target Date | Owner
SC-1 | Escalate supplier availability blockage to customer CXO / executive sponsor. Mandate named supplier SMEs with $\ge$ 40% time commitment via formal SLA. | 2026-08-18 | Cust. Exec Sponsor
SC-2 | If CXO escalation yields no resolution within 3 days, formally recommend structured deferral of this track to M10 with revised Phase 3 dependencies documented. | 2026-08-21 | Impl. PM
SC-3 | In parallel: complete all supplier collaboration solution design with customer proxy SMEs to avoid further design delays once suppliers engage. | 2026-08-22 | Solution Arch
SC-4 | Document full dependency map of Supplier Collaboration on Quality & Change tracks. Present impact to steering committee if deferral is chosen. | 2026-08-19 | Impl. PM
SC-5 | Prepare two plans for steering committee: (A) Accelerated delivery if SMEs secured, (B) Controlled deferral roadmap to M10 with risk summary. | 2026-08-22 | Impl. PM

## Integrations
Action ID | Component | Action Item Description | Target Date | Owner
INT-1 | All | Convene emergency integration war-room: Solution Architect + downstream system leads (SAP, NX, Cadence) + vendor connector owners. Daily 60-min stand-up starting 16-Aug. | 2026-08-16 | Impl. PM
INT-2 | SAP | Finalize data exchange model (BOM structure, ECN payload, material master fields). Customer ERP team and PLM architect to sign off jointly. Hard deadline: 19-Aug. | 2026-08-19 | Sol. Arch
INT-3 | SAP | Run technical approach decision workshop with SAP Basis, middleware (MuleSoft/BTP) team and PLM team. Document agreed approach and get written acceptance from SAP team lead. | 2026-08-20 | Tech Arch
INT-4 | NX | Inventory all version compatibility gaps between PLM platform and NX CAD versions in use. Engage NX vendor for official compatibility matrix. Identify if hotpatch request can be fast-tracked. | 2026-08-19 | NX Lead
INT-5 | NX | Escalate to NX vendor account manager for private hotpatch access or pre-release build to unblock integration layer. Document escalation in writing. | 2026-08-18 | Impl. PM
INT-6 | Cadence | Engage Cadence vendor connector team for integration specification and confirm connector version available for target PLM version. Get written confirmation or documented gap. | 2026-08-20 | Cadence Lead
INT-7 | All | Publish integration dependency & blocker register to steering committee with RAG status per integration point. (Template: Blocker ¦ Root Cause ¦ Owner ¦ Resolution Date ¦ Workaround). | 2026-08-22 | Impl. PM
INT-8 | Joint | Conduct Integration risk review session: classify each blocker as Resolvable (with date) vs Irresolvable. Document workaround for each irresolvable item. | 2026-08-25 | Sol. Arch
INT-9 | Joint | For irresolvable risks: prepare workaround proposals (e.g., file-based interim exchange, manual sync processes, phased go-live without integration, middleware fallback patterns). | 2026-08-26 | Tech Arch
INT-10 | Joint | Present full risk register + workaround proposals to executive steering committee for approval. Obtain sign-off on workarounds or additional escalation path. | 2026-08-27 | Impl. PM
INT-11 | Joint | Revise integration delivery schedule based on approved workarounds. Confirm revised integration milestones and impact on Phase 3 adoption timeline. | 2026-08-29 | Impl. PM

## Data migration
Action ID | Action Item Description | Target Date | Owner
DM-1 | Generate synthetic PLM data set using open-source data fabrication tools (e.g., Faker, Mimesis, custom scripts) modelled on the agreed target data schema. Cover part masters, BOM structures, ECNs, attributes. | 2026-08-18 | DM Lead
DM-2 | Request anonymised production data extracts from customer. Use data masking / PII scrubbing tools on customer side to provide structurally real but privacy-safe records for migration testing. | 2026-08-20 | Cust. DBA
DM-3 | Use existing 90% completed mapping to create a mock legacy extract in the source system format. Populate with synthetic values to simulate full volume migration for FTL testing. | 2026-08-19 | DM Lead
DM-4 | Define acceptance criteria for synthetic data quality. Once real sample extract is available, run delta comparison to validate synthetic data adequacy and calibrate ETL scripts. | 2026-08-22 | QA Lead
DM-5 | Close remaining 10% mapping gap using customer business analyst (BA deployed from stable Part & BOM track) + available documentation. | 2026-08-20 | BA / DM Lead
DM-6 | Evaluate and procure a purpose-built PLM data migration tool (e.g., XPDL, Migrate4PLM, or platform-native migration utilities). Conduct rapid PoC within 3 days. | 2026-08-18 | DM Lead
DM-7 | If commercial tool procurement is blocked, deploy open-source ETL framework (Apache NiFi or Talend Open Studio) configured for PLM source/target schema. | 2026-08-19 | Tech Arch
DM-8 | Implement automated migration reconciliation checks: record count validation, attribute completeness, BOM structure integrity, and delta report after each test run. | 2026-08-22 | QA Lead
DM-9 | Immediate: Engage staffing partner / bench resources to deploy 2 PL/SQL-capable developers by 20-Aug. Require automotive PLM data migration experience. | 2026-08-20 | Delivery VP
DM-10 | Onboarding sprint (Days 1–3): New developers to review existing ETL scripts, mapping docs, and test outputs. Pair with remaining DM team member for knowledge transfer. | 2026-08-22 | DM Lead
DM-11 | Upskill delivery team on platform-native migration APIs in parallel—reduce pure PL/SQL dependency by adopting platform SDK-based migration approach where available. | 2026-08-22 | Tech Arch
DM-12 | Deploy cloud-based developer on-demand resource (AWS/Azure marketplace) as a bridge while permanent hire is finalised. Cost to be approved by delivery VP. | 2026-08-18 | Delivery VP
DM-13 | Conduct team confidence-building session: walkthrough of synthetic data migration success, share test results, define clear individual ownership of each migration object type. | 2026-08-22 | DM Lead
DM-14 | Establish weekly DM-specific war-room: DM Lead + Tech Arch + QA Lead + customer DBA. Track % records migrated, defects per run, blocker status. | 2026-08-19 | Impl. PM